## Summary
Data Governance Delivery Plan
|  | Metadata |  | Data Quality |  | TOTAL
2016 Delivery Options |  | Hours | Cost | Hours | Cost | Hours | Cost
All Activities | TOTAL | 17455 | 1218789 | 20943 | 1684246 | 38398 | 2903035
Option A – Deepen content with existing capabilities (2016) | TIER 1 | 8430 | 575417 | 11568 | 934246 | 19998 | 1509663
Option B – Improve quality of content and improve capabilities (2017+) | TIER 2 | 8205 | 587212 | 9375 | 750000 | 17580 | 1337212
Option C – Strategic Improvements (2017+) | TIER 3 | 820 | 56160 | 0 | 0 | 820 | 56160
TOTAL TIER 1 (2016 PROPOSED) | [5 empty] | 19998 | 1509663
Mid-year alignment on Delivery Plan results in 30% reduced funding request, due to contraints in remaining time and resource availability | [5 empty] | 13998.6 | 1056764.1
Original Budget ($883,000) - Reference Data ($75,000) | [6 empty] | -808000
NET PROPOSED 2016 OVERAGE | [6 empty] | 248764.1
|  | Metadata |  | Data Quality |  | TOTAL
2017 Delivery Options |  | Hours | Cost | Hours | Cost | Hours | Cost
2016 Carryover |  | 2529 | 172625.1 | 3470.4 | 280273.8 | 5999.4 | 452898.9
2017 Funding |  | 9025 | 643372 | 9375 | 750000 | 18400 | 1393372
|  | ======= | ======= | ======= | ======= | ======= | =======
TOTAL 2017 PROPOSED FUNDING |  | 11554 | 815997.1 | 12845.4 | 1030273.8 | 24399.4 | 1846270.9

## 2016 Metadata
Delivery Area | Objective | Category | High-level Activities | Next Level Tasks | Resources | NOTES | Resources | Hours | Cost | Tier | Business Value | Strategic Alignment
1. Metadata Business Glossary Backfill 2016 - Capture, integration, and accessibility of business Metadata | Content |  | 2016 WILL BE LIMITED TO END-TO-END LINEAGE FOR RDR: 1. Deliver the business term identification, creation and linkage for the systems/applications identified as high-priority by the Business, including: MODE-Common, CMIE, RDR-HMDA, RDR Semantic and MIDE integrated. 2. Enrich the business terms by applying standards, removing duplicates and gaining DSO approval to move terms from proposed to reviewed status. 3. Identify and assign Business SMEs to existing systems/applications. | 1. Identify specific linkage gaps by asset, schema, subject area - Review and validate priorities with DSO - Identify overlapping projects that can fill gaps - Assign MDS topic team to build remainder 2. Finalize and socialize Biz Term Name and Definition Standards - Complete removal of proposed terms that are not linked - Validate approach, process and work details for A to Z review of business terms to remove duplicates, cheeseburgers & proposed terms, AND align like business terms by biz term group and Data Steward - Assign MDS topic team to execute - Finalize outline for an all in one business MD "book" - Review and priortize order new "chapters" - Socialize when new "chapters" or updates are finalized 3. Identify assets with no Business SME's - Identify and "on-board" Busi ness SME's | Phill, Victor, MDS, DSO | Phill is developing the detail for these activities and will have draft on Monday. Kim will consult with Phill's team a couple hours a week. Not expecting any resources from my team to be backfilled. Phill take lead. Scope includes any metadata related to RDR lineage | Data Governance Manager Business Metadata Lead Requirements Lead Data Requirements Analysts Metadata Stewards Data Stewards/Business SME Program Manager | 150 | 12000 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
1. Metadata Business Glossary Backfill 2017+ - Capture, integration, and accessibility of business Metadata | Content |  | 1. Deliver the business term identification, creation and linkage for the systems/applications identified as high-priority by the Business, including: MODE-Common, CMIE, RDR-HMDA, RDR Semantic and MIDE integrated. 2. Enrich the business terms by applying standards, removing duplicates and gaining DSO approval to move terms from proposed to reviewed status. 3. Identify and assign Business SMEs to existing systems/applications. |  |  |  | Data Governance Manager Business Metadata Lead Requirements Lead Data Requirements Analysts Metadata Stewards Data Stewards/Business SME Program Manager | 150 | 12000 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
2. Metadata Technical Content Backfill 2016 - Capture, integration, and accessibility of technical Metadata | Content |  | 2016 WILL BE LIMITED TO END-TO-END LINEAGE FOR RDR: 1. Complete the import of 16 new high-priority metadata sources 2. Complete the import of ~7 high-priority MIDE/MODE ETL folders that require analysis and potential modification for accurate lineage 3. Complete extractor to import metadata from ~30 Business Objects reports (including creation of new import feeds) 4. Complete New PowerDesigner extractor and import 15 remaining models (must be aligned with new modeling standards and minimum metadata roll out) 5. Develop training materials, educated and assign Technical Custodians for existing systems/applications in Ab Initio Metadata Hub 6. Enrich existing Systems/Applications with additional metadata, where applicable (e.g. descriptions) | Metadata Technical Content Backfill 2016 - Identify high priority new metadata sources which are part of any data flow to RDR semantic - Shellie/Avinash/Srikanth, 24 hours shared, to be completed in June - Identify high priority new ETL projects which are part of any data flow to RDR semantic - Shellie/Avinash/Srikanth, 24 hours shared, to be completed in June - Identify gap in EDA-EMM accesses to the defined metadata sources - Avinash, 8 hours, to be completed in June - Identify PowerDesigner models associated with metadata sources in any data flow to RDR semantic - Avinash, 16 hours, to be completed in July - Create list of objects which are part of RDR Semantic data flows that are not currently present in metadata hub - Avinash, 16 hours, to be completed in July - Meet with stakeholders to prioritize outstanding metadata imports - Shellie/Avinash, 8 hours shared, to be completed in July - Work with EDA-EMM to establish work plan and timeline for establishing imports for new metadata sources - Shellie/Avinash/EMM, 24 hours shared to be completed in July - Work with EDA-ETL and MODE-ETL to establish a work plan and timeline for resolving all issues related to RDR semantic data flows - Shellie/Srikanth/EMM/ETL, 32 hours shared to be completed in July - Develop overall work plan and timeline for resolving RDR lineage from CORE SOR to RDR Semantic - Shellie/EMM/ETL/Lou/Avinash/Srikanth, 60 hours shared to be completed in July - Identify what data flows are feasible for 2016 and what data flows will carry over into 2017 based on business priority - Technical custodian training will be included in role based training (item 8) below. - Identify hub systems/applications associated with data flows to RDR semantic - Shellie/Phill/EMM/Avinash, 30 hours shared to be completed in September - Evaluate quality of metadata content for the denoted systems/applications - Shellie/Phill/EMM/Avinash, 30 hours to be completed in October - Complete work plan to resolve all issues and implement lineage from CORE SOR to RDR semantic views for high priority RECOR subject areas - Shellie/Srikanth/Lou/EMM/ETL, 1600 hours shared, completed between June and December. | Shellie, Avinash(PT), Jesse(PT) | Please see notes on activities in column E. Avinash and Srikanth would work on this effort and need to be backfilled on projects. I am no longer planning for Jesse to be working on this effort. Shellie take lead. Scope includes any metadata related to RDR lineage | DSG Technology Manager Technical Data Governance Lead Technical Metadata Lead Metadata Analysts ED&A/EMM Manager ED&A/EMM Analysts MODE/MIDE Managers MODE/MIDE ETL Developer MODE/MIDE Data Modeler MIDE ETL Manager Technical Custodian Business Metadata Lead Program Manager | 1880 | 109827 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
2. Metadata Technical Content Backfill 2017+ - Capture, integration, and accessibility of technical Metadata | Content |  | 1. Complete the import of 16 new high-priority metadata sources 2. Complete the import of ~7 high-priority MIDE/MODE ETL folders that require analysis and potential modification for accurate lineage 3. Complete extractor to import metadata from ~30 Business Objects reports (including creation of new import feeds) 4. Complete New PowerDesigner extractor and import 15 remaining models (must be aligned with new modeling standards and minimum metadata roll out) 5. Develop training materials, educated and assign Technical Custodians for existing systems/applications in Ab Initio Metadata Hub 6. Enrich existing Systems/Applications with additional metadata, where applicable (e.g. descriptions) |  |  |  | DSG Technology Manager Technical Data Governance Lead Technical Metadata Lead Metadata Analysts ED&A/EMM Manager ED&A/EMM Analysts MODE/MIDE Managers MODE/MIDE ETL Developer MODE/MIDE Data Modeler MIDE ETL Manager Technical Custodian Business Metadata Lead Program Manager | 1880 | 109827 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
3. Interim State - Metadata Content Delivery as part of Enterprise Releases - Delivery of project Metadata within 4 weeks after enterprise release | Content |  | 1. Refine existing Interim State Process (from R1.16) and incorporate into SDLC 2. Develop/deploy a standard Metadata Task List to be included in the project plans 3. Develop/deliver Project Manager training for the integrated delivery approach; coordinate formal communication with Data Program Leadership 4. Pilot the integrated delivery approach in an upcoming release and deploy in subsequent Enterprise Release | 1. Refine existing Interim State Process (from R1.16) and incorporate into SDLC - Shellie/Jay/Phill/Avinash/Tara, 400 hours shared, to take place between June and July. 2. Develop/deploy a standard Metadata Task List to be included in the project plans - David/Shellie/Phill/Tara/Jay/EMM/ETL, 100 hours, completed in June. 3. Training part of Role directed training (item 8) below. 4. Pilot the integrated delivery approach in an upcoming release and deploy in subsequent Enterprise Release - Shellie/Phill/Tara/Jay/EMM/ETL, 400 hours shared, to take place from July to December | Shellie, Jay, Phill, Tara | Please see notes on activities in column E. Avinash would work on this effort and need to be backfilled on projects. Shellie take lead working with Tara, Phill and Jay. | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead DSG Process Team ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead MODE/MIDE Managers MIDE ETL Manager Business Project Managers Manager Technical Project Managers Manager Metadata Architects Program Manager | 900 | 66100 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
4. Ab Initio Metadata Hub New Connectors/Extractors | Capability |  | 1. Identify, develop and deploy potential enhanced and new extractors for import into Ab Initio Metadata Hub (i.e. XML, MicroStrategy, LPS Cloud, etc.) | Based on results of Metadata Technical Content Backfill 2016 activities above: - Identify high priority new metadata sources which are part of any data flow to RDR semantic - Shellie/Avinash, 16 hours shared, to be completed in June - Identify high priority new ETL projects which are part of any data flow to RDR semantic - included in hours for task above - Identify gap in existing extractors to the defined metadata sources - Avinash, 8 hours to be completed in June - Create list of objects which are part of RDR Semantic data flows that are not currently present in metadata hub - Avinash, 16 hours to be completed in July - Meet with stakeholders to prioritize outstanding metadata import - Shellie/Avinash, 4 hours shared, to be completed in July - Work with Ab Initio to identify new extractors available for import of new object types in RDR lineage - Shellie/Lou/EMM, 15 hours shared, to be completed in July - Work with EDA-EMM to establish work plan and timeline for establishing new extractors for new metadata object types - Shellie/Avinash/EMM, 24 hours shared, to be completed in July - Develop new extractors for new prioritized object types - EMM, 350 hours, to be completed in November - Test and deploy new extractors through lower environments to production - EMM/Avinash, 50 hours, to be completed in December | Shellie, EMM, Avinash (PT) | Please see notes on activities in column E. Avinash would work on this effort and need to be backfilled on projects. Shellie take lead. Scope includes any metadata related to RDR lineage | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 500 | 25250 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Ab Initio Metadata Hub New Capabilities | Capability |  | 1. Identify, develop and deploy potential enhanced and new capabilities of Ab Initio Metadata Hub (separate list provided to ED&A/EMM) | - Verify / consolidate wish list of all HL capability requests - Prioritize (Tier 1, 2 or 3) - Validate priorities with stakeholders - Validate tier 1 sizing / scope with EMM - Validate number and contents of 2016 deliveries | Phill, EMM, Chris, | Phill is developing the detail for these activities and will have draft on Monday. Not expecting any resources from my team, so no need to backfill. Collaborate with EMM for timing and activities. Phill work. | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 1280 | 64640 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Ab Initio Metadata Hub New Capabilities | Capability |  | 1. Identify, develop and deploy potential enhanced and new capabilities of Ab Initio Metadata Hub (separate list provided to ED&A/EMM) |  |  |  | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 720 | 36360 | TIER 2 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Ab Initio Metadata Hub New Capabilities | Capability |  | 1. Identify, develop and deploy potential enhanced and new capabilities of Ab Initio Metadata Hub (separate list provided to ED&A/EMM) |  |  |  | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 320 | 16160 | TIER 3 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
6. Establish Business Driven Metadata Prioritization Process - Establish and formalize governance process to identify & prioritize Business needs for input into delivery and execution activities | Content |  | 1. Leverage available Industry templates and WF guidelines for business prioritization process 2. Document a formal prioritization process to continually engage with the WF Business community and identify, prioritize and manage Business' Metadata needs to help properly sequence delivery/execution activities | 1) Create a backlog chart of all outstanding Home Lending metadata (system and glossary) set to be imported into the Metadata Hub. For each item on the list, document why it was selected to be imported. These 'why' reasons will be known as your current business drivers for Home Lending metadata addition into the MDH. Think of known reasons why Home Lending metadata was added in the past and add those into the 'why' reasons list as well. 40 Hours 2) Fully document how MDH enrichments from Collibra into the MDH are currently being handled. 60 Hours 3) Add future Collibra enrichments into your metadata backlog list of enrichments going into the metadata hub from step one. Include the 'why' reasons again. You documented these 'why' reasons when you met with your Home Lending Collibra rep in step 2. 10 Hours 4) Use known industry templates and practices for backlog prioritization to create a priority heirarchy of the current business drivers you documented in steps 1 and 3. Also use this step to add any industry best business drivers missing from your priority heirarchy. 40 Hours 5) Develop an SLA to communicate availabiltiy in prod of requested metadata by business or technical requestors. SLA will be based on the requested metadata's position on the latest version of the metadata backlog chart. 20 Hours 6) Determine a schedule of how often members of the metadata team need to meet to keep your metadata backlog up to speed. Determine a format for the meetings. If someone from the business has contacted a member of this team with a new metadata addiditon request, not already in the backlog, it should be in this meeting where the new priority heirarhcy is used to add the request into your backlog. 10 Hours | Lou, Shellie, Phill, Aaron | Lou is working to align hours with tasks along with timeline, and we will be discussing resource needs on Monday. I anticipate that he might need help documenting the process and we can leverage one of the Metadata/Data Analysts to do so. This will be require a part time backfill of a metadata resource and run through the end of the year. Lou work and leverage industry best practices and Collibra work on KDEs. Pull in Phill and Tara and input from Kim. | Data Program Leadership Business Governance Manager ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead Metadata Architects Program Manager | 320 | 25600 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
7. Implement Targeted Communication and Status Reporting – Deploy governance, escalation and communication across all program stakeholders | Content & Capability |  | Document a formal communication plan encompassing: 1. Organizational governance model 2. Escalation protocols 3. Status reporting 4. Accountable leader meetings 5. Potential town halls, lunch-n-learn sessions, online/e-mail distributed newsletters, etc. |  |  | Can you please share your content for these activities? I am not planning to assign any resources here. Please let me know if you thought otherwise. David will develop tasks. | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead Program Manager | 300 | 24000 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Seek standardization – opting out is not an option 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
8. Establish Role Based Metadata Training Curriculum for Data Program – Development of training for common Metadata understanding to provide resources in-depth knowledge of practices and processes specific to their role | Content & Capability |  | Develop and deploy training program to: 1. Identify disparate/unique audiences and document each audience's unique training needs 2. Leverage existing training resources to develop and deliver appropriate training materials 3. Establish a SharePoint repository to provide efficient access to the training materials | - Identify different currucila (Biz user, Data Steward, MDS, Compliance User, PM, Tech Custodian, …) - Inventory current training assets (EMM, DP, ...) - Identify courses / content needed for different curricula - Identify gaps training material (the new courses / content needed) - Assign resources to develop & pilot new courses / content - Create, test and approve new courses / content - Assign person to maintain MD training courses / content going forward | Phill, MDS, Jay, EMM | Phill is developing the detail for these activities and will have draft on Monday. Not expecting any resources from my team, so no need to backfill. Phill work on high level plan with input from Jay. | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead Metadata Architects Learning Center Resource Business Intelligence Manager Program Manager | 600 | 48000 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 3. Enable the Best Team in the Mortgage Industry – We will deploy training, tools, and programs to enable and empower our customer-facing team members and supervisors/managers • Job-specific learning paths with clear expectations and documentation of knowledge transfer and proficiency – We will strengthen and improve the quality of our new hires • Strengthen on-boarding process with emphasis on Vision and Values
9. Project Delivery Enablement - Checklists | Capability |  | 1. Leverage available Wells Fargo Enterprise and Home Lending standards to develop tools and templates to capture metadata, including: - Terms: a collection of business names, definitions and attributes with key business information - Objects: a collection of data elements, valid values, defintions and attributes specific to an application, system or physical asset - End-to-End Lineage: flow of data entities between systems and/or applications - Linkage: relationship between business terms and data elements 2. Develop and deploy process and educate users on standards | 1. Identify areas included in scope of review. 2. Identify existing DSG/DP standards. 3. Identify Enterprise Data Governance guidelines required. 4. Identify industry best practices to be leveraged in development of standards. 5. Identify gaps between requirements and documented standards. 6. Modify existing or document new standards within DP. 7. Identify integration points and milestones in SDLC process. 7. Develop plan for implementing new standards. 8. Communicate and implement new standards and processes. | Tara, Shellie, Jay, Lou, Kim, Phill, Jesse (PT) | Will be meeting with Tara on Monday to discuss this. She has been workiing on Data Governance with Ann and I think her work there will tie into these activities, but we have not been able to meet to determine possible connections. We will do that Monday. Once I have a better idea of what she is focused on, we will get a better idea of what is outstanding, the approach and timeline for completing these activities. It will most likely involve a Data Analyst for documentation purposes. We have talked about utilizing someone from her team rather than mine, but I'm unsure if that means she needs to backfill. I am no longer planning to utilize Jesse here. Tara take lead and Shellie assist. | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers Metadata Architects Program Manager | 1000 | 80000 | TIER 1 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Seek standardization – opting out is not an option – Identify and execute on simplification opportunities • Accelerate product and program simplification 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
10. Project Delivery Enablement - Tool Enhancements | Capability | EMETR: Ab Initio's ETL Technical Repository (Enterprise Meta Evironment Techncial Repository)which stores the DDLs, GRAPHs and PSETs used for the Ab Initio ETL and leveraged by Ab Initio's Metadata Hub to import ETL-related Metadata | 1.Review the existing processes that determine how the EME TR is leveraged to provide Ab Initio ETL-related informaton for import into the Ab Initio Metadata Hub. 2. How is EME TR leveraged to deliver on the overall Data Program Strategy 3. Document and identify gaps 4. Develop a mitigation plan and timeline |  |  |  | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead MIDE/MODE Managers MIDE/MODE Modelers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
10. Project Delivery Enablement - Tool Enhancements | Capability | EMH: Ab Initio's Metadata Hub used to import, persist, manage, display and report on Metadata information imported from various sources | 1.Review existing processes and approach for how Ab Initio Metadata Hub is configured. 2. How it integrates with other tools in the Ab Initio Suite. 3. How it is Ab Initio Metadata Hub leveraged to deliver on the overall Data Program Strategy 4. Document and identify gaps 5. Develop a mitigation plan and timeline |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
10. Project Delivery Enablement - Tool Enhancements | Capability | Power Designer: Data Modelling tool used to model data structures for the Metadata Hub and align them with the data structures in use by the production systems and/or applications | 1.Review existing processes and approach for how Home Lending leverages Power Designer to maintain, develop and import models into AB Initio Metadata Hub 2.Identify the opportunity to implement more stringent data modeling standards to better align the Metadata data modeling efforts with the Enterprise Release data modeling 3. How is PowerDesigner leveraged to deliver on the overall Data Program Strategy 4. Document and idetified gaps 5. Develop a mitigation plan and timeline |  |  |  | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead MIDE/MODE Managers MIDE/MODE Modelers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
10. Project Delivery Enablement - Tool Enhancements | Capability | Excel: MS Tool is used to develop manual mappings for those Metadata sources which the Ab Initio Metadata Hub cannot run automatic extract and import functionality | 1.Review existing processes and approach for how Home Lending uses connectors and capabilities to automate import of disparate Metadata sources (e.g. Excel) 2. Evaluate the opportunity to use other solutions for a more automated Metadata import 3. How is Excel (or other tool) leveraged to deliver on the overall Data Program Strategy 4. Document and idetified gaps 5. Develop a mitigation plan and timeline |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE/MODE Mappers/Developers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
11. Project Delivery Enablement - Lower Environment Capability Assessment | Capability | Assessment/Gap Analysis | 1. Review ED&A-deployed processes and procedures for the lower environments which control the technical architecture, environmental configuration, Ab Initio Metadata Hub configuration and content refresh approach 2. Document gaps identified during the Assessment and capture opportunities to more closely align the lower environments with the production environment | 1. Schedule meetings with ED&A and EMM to gain an understanding of the existing lower environment technology infrastructure include the hardware and software through a review of the existing systems - Jay, Shellie, Lou, John Holzworth, Shalini Carney -40 Hours 2. Identify the requirements (Hardware, Software, Network, Storage) for lower environment for effective Metadata Management as stated in the Metadata Vision - John H, Shalini C, Infrastructure Architects, Jay , Shellie, Lou - 80 hours 3. Document the gaps between the existing infrastructure and the required infrastructure - EMM, ED&A resources, Metadata team - 120 Hours 4. Reviews the Gap Analysis documens with the stakeholders for confirmation prior to preparing the recommendations for remediation - 40 hours | Jay, Lou, John Holzwarth, EMM Analyst | Jay is going to break out the hours for the tasks and then we will work together to come up with a schedule. It will not include any resources from my team and thus does not require backfill. | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE ETL Manager MIDE/MODE ETL Developers Metadata Architects Program Manager | 750 | 60000 | TIER 1 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
11. Project Delivery Enablement - Lower Environment Capability Assessment | Capability | Remediation | 1. Develop and a prioritized remediation plan to methodically address gaps identified in the assessment |  |  |  | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE ETL Manager MIDE/MODE ETL Developers Metadata Architects Program Manager | 500 | 40000 | TIER 3 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
12. Build Taxonomy 2016 | Capability | Technical Business Subject Area Tags | 1. Review and understand current taxonomy 2. Leverage industry standard taxonomy models 3. Interview key business and technical resources to determine their needs 4. Propose an appropriate taxonomy for Home Lending 5. Develop phased timeline for deployment of taxonomy | 1) Create a chart of known user experience issues within the metadata hub by meeting with our mangement and anyone they recommend us to. 40 Hours 2) Leveraging Shellie and Jay's chart of anticpated future Metadata Users and Use Cases, identify which newly created Use Case will addess each user experience issue charted in step 1. 60 Hours 3) Work with Ab Initio and ED&A to determine the best apporach on how to realize these new Use Cases in the metadata Hub backend. If the selected approach requires altering Ab initio's MDH solution, approach ED&A with these suggested approaches for approval and if approved, implementation timelies. 400 Hours 4) Apply the new Use Case "roles" to a limited set of current Home Lending MDH users as a proof of concept of the new system. Will most likely be individuals involved in the creation of this spreadsheet. Take feedback, and make adjustments where necessary. 50 Hours 5) Create a communication plan and implementation plan for your new limited taxonomy approach for the rest of your Home Lending MDH users. Prioritize implementation by fixing the most pressing and often reported issues documented in step 1. 50 Hours | Lou, Jay, Phill, Tony P. | Lou is working on redeveloping this item with the clarified approach shared by Chris and the decline of the logical model POC. I will be meeting with him on Monday to review his output. This work will most likely involve Lou, Phill and EMM, so we do not need any backfill resources. make sure you put items on here like : get known use cases from business uses of where the current taxonomy is not supporting their needs. | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmt/Metadata MIDE/MODE Managers MIDE/MODE Analysts Metadata Architects Program Manager | 750 | 60000 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Think horizontally and end-to-end – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
12. Build Taxonomy 2017 | Capability | Technical Business Subject Area Tags | 1. Review and understand current taxonomy 2. Leverage industry standard taxonomy models 3. Interview key business and technical resources to determine their needs 4. Propose an appropriate taxonomy for Home Lending 5. Develop phased timeline for deployment of taxonomy |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmt/Metadata MIDE/MODE Managers MIDE/MODE Analysts Metadata Architects Program Manager | 750 | 60000 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Think horizontally and end-to-end – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
13. Governance - Build SDLC Tollgate Process | Capability | - Acceptance Criteria - Exception Criteria and Approval Level | 1. Develop and deploy enhancements to the Enterprise Release SDLC standard acceptance and exception criteria and its approvals to ensure: - Metadata activities are completed as expected - Business & Technical Metadata is properly imported into the Ab Initio Metadata Hub - Functionality of the tool properly displays the desired results for user consumption |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead Data Quality Lead MIDE/MODE Managers Business Intelligence Manager Release Manager Metadata Architects Program Manager | 500 | 40000 | TIER 2 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
13. Governance - Build SDLC Tollgate Process | Capability | Roles & Responsibilities | 1. Document, obtain approval and communicate Roles & Responsibiities for all participants in the Metadata process 2. Align the roles within the established workstream and leverage documentation used for RESPA/TILA EOC |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead Data Quality Lead Data Analyst - Rqmts/Metadata MIDE/MODE Managers Business Intelligence Manager Release Manager Metadata Architects Program Manager | 300 | 24000 | TIER 2 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
14. Governance - Risk Management | Capability | Metadata Reporting (lineage, completeness, etc.) Flexibility to utilize reporting to establish quantitative and qualitative Metadata measurement | 1. Identify the Quantitative and Qualitative Metrics required for Metadata quality 2. Conduct Validation Reporting POC 3. Leverage POC results to identify appropriate toolset, approach and resources required 4. Develop timeline for validation reporting effort 5. Build and deploy Metadata quality reports NOTE: Estimate assumes 10 initial reports of medium complexity |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Quality Lead Metadata Architects Program Manager | 905 | 65025 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
15. Governance - Data Asset Reuse | Capability | Lifecycle Management •New Terms (proposed, candidate, approved, deprecated, etc.) •Term Conflict management, overloading, context collision •New SOR data | 1. Define new and enhance existing Home Lending metadata governance processes, leveraging industry best practices 2. Communicate and deploy defined governance processes |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmts/Metadata Metadata Architects Data Steward (DSO) Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification – Effectively translate investor, regulatory, and legal guidelines into policy and process
15. Governance - Data Asset Reuse | Capability | Data Asset Reuse: - Shared Dataset creation - Detailed level associations | 1. Identify existing shared data assets and opportunities for modifying data assets to make reusable 2. Establish standards to support ongoing reuse of data assets |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE/MODE Developers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
16. Usability - Locate Data Faster | Capability | Query/Report creation - Results grouped and ordered by tags | Develop & deploy a user-friendly query/reporting solution to provide rapid access to commonly needed Metadata information 1. Define business requirements for accessing metadata - include ability to group and order by tags - limit result set 2. Identify toolset and develop solution through POC - Engage users for trial and feedback 3. Develop timeline for deployment of final solution including end-user training |  |  |  | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmt/Metadata Business Intelligence Manager Business Intelligence Engineers Metadata Architects Program Manager | 1200 | 96000 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification 3. Enable the Best Team in the Mortgage Industry – We will deploy training, tools, and programs to enable and empower our customer-facing team members and supervisors/managers • Job-specific learning paths with clear expectations and documentation of knowledge transfer and proficiency – We will strengthen and improve the quality of our new hires • Strengthen on-boarding process with emphasis on Vision and Values
|  |  | 2016 Delivery Options |  |  |  |  | Hours | Cost
|  |  | All Activities |  |  |  | TOTAL | 17455 | 1218789
|  |  | Option A – Deepen content with existing capabilities |  |  |  | TIER 1 | 8430 | 575417
|  |  | Option B – Improve quality of content and improve capabilities |  |  |  | TIER 2 | 8205 | 587212
|  |  | Option C – Strategic Improvements |  |  |  | TIER 3 | 820 | 56160
Role |  | Currently in Role
Business Intelligence Manager |  | Saundra Formanek
Business Metadata Lead |  | Phill Karabinus
Business Project Manager - Lead |  | Tom Huisman
Data Governance Manager |  | Saad Ahmed
Data Program Leadership |  | Ashish Lahoti Dawn Henson Karin Zahorik Nate Strickler
Data Quality Lead |  | Ron Jones
DSG Process Team |  | Audra Kneer
DSG Technology Manager |  | Chris Walsh
ED&A/EMM Manager |  | John Holzwarth
Metadata Architects |  | Kim Bare Louis Puskas
MIDE ETL Manager |  | Shalini Carney
MODE/MIDE Managers |  | David Kuhn(MODE) Randy Chumbley(MODE) Ann Summers(MIDE)
Program Manager |  | David Stern
Release Manager |  | Sunny Stone
Requirements Lead |  | Tara Bettis
Technical Custodian |  | Application Owners
Technical Data Governance Lead |  | Jayanta Sengupta
Technical Metadata Lead |  | Shellie Kaiser
Technical Project Manager - Lead |  | Jona Khandekar

## 2016 Data Quality
2016 Data Quality Delivery Plan
Delivery Area | Objective | Category | High-level Activities | Resources | Hours | Cost | Tier | Business Value | Strategic Alignment
1. Define Data Quality Foundational Requirements - Define & implement a repeatable DQ Approach & Controls in SDLC methodology, including threshold limits, exception criteria and verification process for validating the accuracy of data elements of in-scope projects. | Capability | Test Data Management | 1. Develop and deploy a repeatable Data Quality - Test Data Management Strategy, including: - Develop Processes, Tools & Templates, to manage testing plans, expectations and actual results - Analyze Test Data requirements for in-scope testing scenarios - Determine Test Data sources required for in-scope testing scenarios - Extract subset of test data from production SORs/systems to support in-scope scenarios - Mask/sanitize test data to prepare for repeatable testing - Determine frequency of Test Data refresh from Production into Testing environment(s) | Data Governance Manager DSG Technology manager ED&A/EMM Manager MIDE/ETL Manager MODE/ETL Manager Data Quality Lead CCC/QA Lead Requirements Lead Technical Data Governance Lead Metadata Architects Program Manager | 6250 | 500000 | TIER 1 | b. Improved project delivery quality through the implementation test data management and automated data validation frameworks | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 2. Understand, Measure, and Manage Risk – Strengthen our risk management culture • Operate within defined risk appetite standards, with preventative controls in place
1. Define Data Quality Foundational Requirements - Define & implement a repeatable DQ Approach & Controls in SDLC methodology, including threshold limits, exception criteria and verification process for validating the accuracy of data elements of in-scope projects. | Capability | Data Validation Framework | 1. Develop and deploy a repeatable Data Validation Framework, including: - Select tool to automate Data Validation testing (i.e. Ab Initio, VB net, etc.) - Develop/deploy Processes, Tools & Templates, to automate Data Validation testing - Develop positive and negative testing scenarios - Develop Anomaly resolution processes to address gaps identified during test execution - Compare the Baseline Data with the Test Data (regression testing) - Capture any data anomalies and inconsistencies identified during test execution - Report on Data Validation results for data anomaly resolution | Data Governance Manager DSG Technology manager ED&A/EMM Manager MIDE/ETL Manager MODE/ETL Manager Data Quality Lead Data Quality Analysts CCC/QA Lead Technical Data Governance Lead Metadata Architects Program Manager | 6250 | 500000 | TIER 2 | b. Improved project delivery quality through the implementation test data management and automated data validation frameworks | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place
1. Define Data Quality Foundational Requirements - Define & implement a repeatable DQ Approach & Controls in SDLC methodology, including threshold limits, exception criteria and verification process for validating the accuracy of data elements of in-scope projects. Collection of the Quantitative metrics - Collect Quantitative metrics for MIDE & MODE, in addition to Qualitative metrics currently being collected for MIDE. | Capability | Data Integrity Monitoring (Operational Console) | 1. Develop and deploy a Data Integrity Monitoring framework, including: - Develop/deploy Processes, Tools & Templates for Data Integrity Monitoring - Develop Anomaly resolution processes to address identified gaps - Establish the Quantitative metrics, including defined monitoring thresholds - Implement Data Integrity Monitoring execution at pre-determined frequencies - Capture any anomalies or inconsistencies identified during Data Integrity Monitoring - Report on Data Integrity results for anomaly resolution 2. Leverage existing Quantitative testing capabiities & Dashboard from CORE 3. Enhance DQE for MIDE & MODE to incorporate Quantitative monitoring & reporting of metrics 4. Review and adjust DQE access rights for appropriate role-based views 5. Enable Quantitative Data Validation & Remediation via DQE Tool 6. Enhance import of DQE Quantitative Scoring results into the Metadata Hub at the KDE level | Data Governance Manager DSG Technology manager ED&A/EMM Manager ED&A/EMM Analyst MIDE/ETL Manager MODE/ETL Manager Data Quality Lead Data Quality Analysts CCC/QA Lead Technical Data Governance Lead Metadata Architects Program Manager | 3125 | 250000 | TIER 2 | c. Ensure data completeness and fit for use via data integrity monitoring of data transmission and processing activity | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place
2. Operational DQ process & procedures – Develop and implement a standard, streamlined process for Operational DQ. (begun in 2015) | Capability |  | This activity is part of the overall Data Quality efforts. Implement Data Quality monitoring by the Data Quality team 1. Review existing Operational Data Quality processes and determine enhancement requirements 2. Leverage industry best-practice standards, tools & templates, as required 3. Enhance documented processes & procedures for future state Operational Data Quality 4. Empower Business users to leverage Operational Data Quality metrics | Data Governance Manager DSG Technology manager Data Quality Lead Requirements Lead Metadata Architects Program Manager | 680 | 52040 | TIER 1 | a. Leverage Data Quality scoring techniques to improve customer delight by isolating data issues at the point of capture and ensure data accuracy for regulatory, operational, and financial risk reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
3. DQE tool implementation for MODE – Implement the DQE tool for MODE, similar to the R4.15 implementation of DQE for MIDE. | Content & Capability |  | 1. Enhance DQE implementation for MODE to incorporate broader scope of SORs/Systems 2. Review and adjust DQE access rights for appropriate role-based views 3. Enable Qualitative Data Validation & Remediation via DQE Tool 4. Enhance import of DQE Qualitative Scoring results into the Metadata Hub at the KDE level | Data Governance Manager DSG Technology manager ED&A/EMM Manager MIDE/MODE ETL Managers Data Quality Lead Metadata Architects Program Manager | 1638 | 142206 | TIER 1 | a. Leverage Data Quality scoring techniques to improve customer delight by isolating data issues at the point of capture and ensure data accuracy for regulatory, operational, and financial risk reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
4. Collection of Key Data Elements (“KDEs”) and DQ rules - KDEs will be collected and DQ Rules implemented for implemented projects. | Content & Capability |  | This activity is a predecessor to DQ Reporting via Dashboard and a required Business value-add Implement Data Quality scoring at the MIDE Source level by the Data Quality team 1. During the Requirements gathering process, capture the top ~25 KDEs for each system a. Identification of the top ~25 KDEs for each system by the Business consumers of the system. b. Verification and approval of the top ~25 KDEs for each system ONLY by the Data Steward Organization, who represent the data consumption group (RECOR: Janaki/Adeel, Capital Markets: Bob Schmidt, Credit Risk Management: Rajeshri, etc.). 2. During the Requirements gathering process: a. Capture the Data Quality rules for the top ~25 KDEs, by the Business consumers of the system b. Data Quality rules must be verified by Data Owners or Data Stewards (Retail/CORE & LIS: Ann Brown, Correspondent/LPS: Matt Barrett, Capital Markets Finance: Risk Arnold, etc.) correspondent/ LPS system) c. Obtain agreement and alignment on Data Quality rules development logic and data delivery expectations from consumers, to ensure low error results 3. During the Design/Development phases: a. Implement the Data Quality rules for the top ~25 KDEs, by the Data Quality team b. Using the Data Quality rules, conduct Data Validation testing and Data Quality scoring against the Target and Source system, by the Data Quality team NOTE: Estimate assumes 5 initial key systems | Data Governance Manager DSG Technology Manager Business Metadata Lead Requirements Lead Data Quality Lead Program Manager | 1200 | 96000 | TIER 1 | a. Leverage Data Quality scoring techniques to improve customer delight by isolating data issues at the point of capture and ensure data accuracy for regulatory, operational, and financial risk reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Additional DQ Reporting via Dashboard - Reporting will include enhancements to existing DQ reports, consumer facing Data Quality metrics & Trending, Usage metrics and Data Validation. | Content & Capability |  | This activity is a successor to Collection of KDEs & DQ Rules and a required Business value-add 1. Leverage results of the Dashboard reporting POC and enhance as necessary 2. Determine pilot group of 10 Dashboard Reports 3. Develop deployment workplan and timeline 4. Build and deploy the initial 10 Data Quality metrics, scoring and validation reports | Data Program Leadership Data Program Strategist Data Governance Manager DSG Technology Manager Business Metadata Lead Technical Metadata Lead Data Quality Lead Business Intelligence Manager Business Intelligence Engineer Solution Engineer Program Manager | 1200 | 96000 | TIER 1 | a. Leverage Data Quality scoring techniques to improve customer delight by isolating data issues at the point of capture and ensure data accuracy for regulatory, operational, and financial risk reporting b. Improved project delivery quality through the implementation test data management and automated data validation frameworks c. Ensure data completeness and fit for use via data integrity monitoring of data transmission and processing activity | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents
6. Additional Training for Analysts – To integrate the DQE tool into the Metadata SDLC, extend tool usage to include Data Analysts. | Capability |  | Develop and deploy training program to: 1. Identify disparate/unique audiences and document each audience's unique training needs 2. Leverage existing training resources to develop and deliver appropriate training materials 3. Establish a SharePoint repository to provide efficient access to the training materials | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead Business Metadata Lead Technical Metadata Lead Requirements Lead Metadata Architects Learning Center Resource Business Intelligence Manager Program Manager | 600 | 48000 | TIER 1 | a. Leverage Data Quality scoring techniques to improve customer delight by isolating data issues at the point of capture and ensure data accuracy for regulatory, operational, and financial risk reporting b. Improved project delivery quality through the implementation test data management and automated data validation frameworks c. Ensure data completeness and fit for use via data integrity monitoring of data transmission and processing activity | 3. Enable the Best Team in the Mortgage Industry – We will deploy training, tools, and programs to enable and empower our customer-facing team members and supervisors/managers • Job-specific learning paths with clear expectations and documentation of knowledge transfer and proficiency – We will strengthen and improve the quality of our new hires • Strengthen on-boarding process with emphasis on Vision and Values
|  |  | 2016 Delivery Options |  | Hours | Cost
|  |  | All Activities | TOTAL | 20943 | 1684246
|  |  | Option A – Deepen content with existing capabilities | TIER 1 | 11568 | 934246
|  |  | Option B – Improve quality of content and improve capabilities | TIER 2 | 9375 | 750000
|  |  | Option C – Strategic Improvements | TIER 3 | 0 | 0
Role |  | Currently in Role
Business Intelligence Manager |  | Saundra Formanek
Business Metadata Lead |  | Phill Karabinus
Business Project Manager - Lead |  | Tom Huisman
Data Governance Manager |  | Saad Ahmed
Data Program Leadership |  | Ashish Lahoti Dawn Henson Karin Zahorik Nate Strickler
Data Quality Lead |  | Ron Jones
DSG Process Team |  | Audra Kneer
DSG Technology Manager |  | Chris Walsh
ED&A/EMM Manager |  | John Holzwarth
Metadata Architects |  | Kim Bare Louis Puskas
MIDE ETL Manager |  | Shalini Carney
MODE/MIDE Managers |  | David Kuhn(MODE) Randy Chumbley(MODE) Ann Summers(MIDE)
Program Manager |  | David Stern
Release Manager |  | Sunny Stone
Requirements Lead |  | Tara Bettis
Technical Custodian |  | Application Owners
Technical Data Governance Lead |  | Jayanta Sengupta
Technical Metadata Lead |  | Shellie Kaiser
Technical Project Manager - Lead |  | Jona Khandekar

## Metadata
Delivery Area | Objective | Category | High-level Activities | Resources | Hours | Cost | Tier | Business Value | Strategic Alignment
1. Metadata Business Glossary Backfill 2016 - Capture, integration, and accessibility of business Metadata | Content |  | 2016 WILL BE LIMITED TO END-TO-END LINEAGE FOR RDR: 1. Deliver the business term identification, creation and linkage for the systems/applications identified as high-priority by the Business, including: MODE-Common, CMIE, RDR-HMDA, RDR Semantic and MIDE integrated. 2. Enrich the business terms by applying standards, removing duplicates and gaining DSO approval to move terms from proposed to reviewed status. 3. Identify and assign Business SMEs to existing systems/applications. | Data Governance Manager Business Metadata Lead Requirements Lead Data Requirements Analysts Metadata Stewards Data Stewards/Business SME Program Manager | 150 | 12000 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
1. Metadata Business Glossary Backfill 2017+ - Capture, integration, and accessibility of business Metadata | Content |  | 1. Deliver the business term identification, creation and linkage for the systems/applications identified as high-priority by the Business, including: MODE-Common, CMIE, RDR-HMDA, RDR Semantic and MIDE integrated. 2. Enrich the business terms by applying standards, removing duplicates and gaining DSO approval to move terms from proposed to reviewed status. 3. Identify and assign Business SMEs to existing systems/applications. | Data Governance Manager Business Metadata Lead Requirements Lead Data Requirements Analysts Metadata Stewards Data Stewards/Business SME Program Manager | 150 | 12000 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
2. Metadata Technical Content Backfill 2016 - Capture, integration, and accessibility of technical Metadata | Content |  | 2016 WILL BE LIMITED TO END-TO-END LINEAGE FOR RDR: 1. Complete the import of 16 new high-priority metadata sources 2. Complete the import of ~7 high-priority MIDE/MODE ETL folders that require analysis and potential modification for accurate lineage 3. Complete extractor to import metadata from ~30 Business Objects reports (including creation of new import feeds) 4. Complete New PowerDesigner extractor and import 15 remaining models (must be aligned with new modeling standards and minimum metadata roll out) 5. Develop training materials, educated and assign Technical Custodians for existing systems/applications in Ab Initio Metadata Hub 6. Enrich existing Systems/Applications with additional metadata, where applicable (e.g. descriptions) | DSG Technology Manager Technical Data Governance Lead Technical Metadata Lead Metadata Analysts ED&A/EMM Manager ED&A/EMM Analysts MODE/MIDE Managers MODE/MIDE ETL Developer MODE/MIDE Data Modeler MIDE ETL Manager Technical Custodian Business Metadata Lead Program Manager | 1880 | 109827 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
2. Metadata Technical Content Backfill 2017+ - Capture, integration, and accessibility of technical Metadata | Content |  | 1. Complete the import of 16 new high-priority metadata sources 2. Complete the import of ~7 high-priority MIDE/MODE ETL folders that require analysis and potential modification for accurate lineage 3. Complete extractor to import metadata from ~30 Business Objects reports (including creation of new import feeds) 4. Complete New PowerDesigner extractor and import 15 remaining models (must be aligned with new modeling standards and minimum metadata roll out) 5. Develop training materials, educated and assign Technical Custodians for existing systems/applications in Ab Initio Metadata Hub 6. Enrich existing Systems/Applications with additional metadata, where applicable (e.g. descriptions) | DSG Technology Manager Technical Data Governance Lead Technical Metadata Lead Metadata Analysts ED&A/EMM Manager ED&A/EMM Analysts MODE/MIDE Managers MODE/MIDE ETL Developer MODE/MIDE Data Modeler MIDE ETL Manager Technical Custodian Business Metadata Lead Program Manager | 1880 | 109827 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
3. Interim State - Metadata Content Delivery as part of Enterprise Releases - Delivery of project Metadata within 4 weeks after enterprise release | Content |  | 1. Refine existing Interim State Process (from R1.16) and incorporate into SDLC 2. Develop/deploy a standard Metadata Task List to be included in the project plans 3. Develop/deliver Project Manager training for the integrated delivery approach; coordinate formal communication with Data Program Leadership 4. Pilot the integrated delivery approach in an upcoming release and deploy in subsequent Enterprise Release | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead DSG Process Team ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead MODE/MIDE Managers MIDE ETL Manager Business Project Managers Manager Technical Project Managers Manager Metadata Architects Program Manager | 900 | 66100 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
4. Ab Initio Metadata Hub New Connectors/Extractors | Capability |  | 1. Identify, develop and deploy potential enhanced and new extractors for import into Ab Initio Metadata Hub (i.e. XML, MicroStrategy, LPS Cloud, etc.) | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 500 | 25250 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Ab Initio Metadata Hub New Capabilities | Capability |  | 1. Identify, develop and deploy potential enhanced and new capabilities of Ab Initio Metadata Hub (separate list provided to ED&A/EMM) | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 1280 | 64640 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Ab Initio Metadata Hub New Capabilities | Capability |  | 1. Identify, develop and deploy potential enhanced and new capabilities of Ab Initio Metadata Hub (separate list provided to ED&A/EMM) | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 720 | 36360 | TIER 2 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
5. Ab Initio Metadata Hub New Capabilities | Capability |  | 1. Identify, develop and deploy potential enhanced and new capabilities of Ab Initio Metadata Hub (separate list provided to ED&A/EMM) | DSG Technology Manager Data Governance Manager Technical Data Governance Lead Technical Metadata Lead Business Metadata Lead Metadata Architect ED&A/EMM Manager ED&A/EMM Analysts Program Manager | 320 | 16160 | TIER 3 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
6. Establish Business Driven Metadata Prioritization Process - Establish and formalize governance process to identify & prioritize Business needs for input into delivery and execution activities | Content |  | 1. Leverage available Industry templates and WF guidelines for business prioritization process 2. Document a formal prioritization process to continually engage with the WF Business community and identify, prioritize and manage Business' Metadata needs to help properly sequence delivery/execution activities | Data Program Leadership Business Governance Manager ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead Metadata Architects Program Manager | 320 | 25600 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
7. Implement Targeted Communication and Status Reporting – Deploy governance, escalation and communication across all program stakeholders | Content & Capability |  | Document a formal communication plan encompassing: 1. Organizational governance model 2. Escalation protocols 3. Status reporting 4. Accountable leader meetings 5. Potential town halls, lunch-n-learn sessions, online/e-mail distributed newsletters, etc. | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead Program Manager | 300 | 24000 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Seek standardization – opting out is not an option 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
8. Establish Role Based Metadata Training Curriculum for Data Program – Development of training for common Metadata understanding to provide resources in-depth knowledge of practices and processes specific to their role | Content & Capability |  | Develop and deploy training program to: 1. Identify disparate/unique audiences and document each audience's unique training needs 2. Leverage existing training resources to develop and deliver appropriate training materials 3. Establish a SharePoint repository to provide efficient access to the training materials | Data Program Leadership Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager Business Metadata Lead Technical Metadata Lead Requirements Lead Metadata Architects Learning Center Resource Business Intelligence Manager Program Manager | 600 | 48000 | TIER 1 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 3. Enable the Best Team in the Mortgage Industry – We will deploy training, tools, and programs to enable and empower our customer-facing team members and supervisors/managers • Job-specific learning paths with clear expectations and documentation of knowledge transfer and proficiency – We will strengthen and improve the quality of our new hires • Strengthen on-boarding process with emphasis on Vision and Values
9. Project Delivery Enablement - Checklists | Capability |  | 1. Leverage available Wells Fargo Enterprise and Home Lending standards to develop tools and templates to capture metadata, including: - Terms: a collection of business names, definitions and attributes with key business information - Objects: a collection of data elements, valid values, defintions and attributes specific to an application, system or physical asset - End-to-End Lineage: flow of data entities between systems and/or applications - Linkage: relationship between business terms and data elements 2. Develop and deploy process and educate users on standards | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers Metadata Architects Program Manager | 1000 | 80000 | TIER 1 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Seek standardization – opting out is not an option – Identify and execute on simplification opportunities • Accelerate product and program simplification 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
10. Project Delivery Enablement - Tool Enhancements | Capability | EMETR: Ab Initio's ETL Technical Repository (Enterprise Meta Evironment Techncial Repository)which stores the DDLs, GRAPHs and PSETs used for the Ab Initio ETL and leveraged by Ab Initio's Metadata Hub to import ETL-related Metadata | 1.Review the existing processes that determine how the EME TR is leveraged to provide Ab Initio ETL-related informaton for import into the Ab Initio Metadata Hub. 2. How is EME TR leveraged to deliver on the overall Data Program Strategy 3. Document and identify gaps 4. Develop a mitigation plan and timeline | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead MIDE/MODE Managers MIDE/MODE Modelers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
10. Project Delivery Enablement - Tool Enhancements | Capability | EMH: Ab Initio's Metadata Hub used to import, persist, manage, display and report on Metadata information imported from various sources | 1.Review existing processes and approach for how Ab Initio Metadata Hub is configured. 2. How it integrates with other tools in the Ab Initio Suite. 3. How it is Ab Initio Metadata Hub leveraged to deliver on the overall Data Program Strategy 4. Document and identify gaps 5. Develop a mitigation plan and timeline | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
10. Project Delivery Enablement - Tool Enhancements | Capability | Power Designer: Data Modelling tool used to model data structures for the Metadata Hub and align them with the data structures in use by the production systems and/or applications | 1.Review existing processes and approach for how Home Lending leverages Power Designer to maintain, develop and import models into AB Initio Metadata Hub 2.Identify the opportunity to implement more stringent data modeling standards to better align the Metadata data modeling efforts with the Enterprise Release data modeling 3. How is PowerDesigner leveraged to deliver on the overall Data Program Strategy 4. Document and idetified gaps 5. Develop a mitigation plan and timeline | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead MIDE/MODE Managers MIDE/MODE Modelers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
10. Project Delivery Enablement - Tool Enhancements | Capability | Excel: MS Tool is used to develop manual mappings for those Metadata sources which the Ab Initio Metadata Hub cannot run automatic extract and import functionality | 1.Review existing processes and approach for how Home Lending uses connectors and capabilities to automate import of disparate Metadata sources (e.g. Excel) 2. Evaluate the opportunity to use other solutions for a more automated Metadata import 3. How is Excel (or other tool) leveraged to deliver on the overall Data Program Strategy 4. Document and idetified gaps 5. Develop a mitigation plan and timeline | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE/MODE Mappers/Developers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
11. Project Delivery Enablement - Lower Environment Capability Assessment | Capability | Assessment/Gap Analysis | 1. Review ED&A-deployed processes and procedures for the lower environments which control the technical architecture, environmental configuration, Ab Initio Metadata Hub configuration and content refresh approach 2. Document gaps identified during the Assessment and capture opportunities to more closely align the lower environments with the production environment | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE ETL Manager MIDE/MODE ETL Developers Metadata Architects Program Manager | 750 | 60000 | TIER 1 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
11. Project Delivery Enablement - Lower Environment Capability Assessment | Capability | Remediation | 1. Develop and a prioritized remediation plan to methodically address gaps identified in the assessment | DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE ETL Manager MIDE/MODE ETL Developers Metadata Architects Program Manager | 500 | 40000 | TIER 3 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
12. Build Taxonomy 2016 | Capability | Technical Business Subject Area Tags | 1. Review and understand current taxonomy 2. Leverage industry standard taxonomy models 3. Interview key business and technical resources to determine their needs 4. Propose an appropriate taxonomy for Home Lending 5. Develop phased timeline for deployment of taxonomy | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmt/Metadata MIDE/MODE Managers MIDE/MODE Analysts Metadata Architects Program Manager | 750 | 60000 | TIER 1 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Think horizontally and end-to-end – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
12. Build Taxonomy 2017 | Capability | Technical Business Subject Area Tags | 1. Review and understand current taxonomy 2. Leverage industry standard taxonomy models 3. Interview key business and technical resources to determine their needs 4. Propose an appropriate taxonomy for Home Lending 5. Develop phased timeline for deployment of taxonomy | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmt/Metadata MIDE/MODE Managers MIDE/MODE Analysts Metadata Architects Program Manager | 750 | 60000 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Think horizontally and end-to-end – Identify and execute on simplification opportunities • Accelerate product and program simplification 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
13. Governance - Build SDLC Tollgate Process | Capability | - Acceptance Criteria - Exception Criteria and Approval Level | 1. Develop and deploy enhancements to the Enterprise Release SDLC standard acceptance and exception criteria and its approvals to ensure: - Metadata activities are completed as expected - Business & Technical Metadata is properly imported into the Ab Initio Metadata Hub - Functionality of the tool properly displays the desired results for user consumption | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead Data Quality Lead MIDE/MODE Managers Business Intelligence Manager Release Manager Metadata Architects Program Manager | 500 | 40000 | TIER 2 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
13. Governance - Build SDLC Tollgate Process | Capability | Roles & Responsibilities | 1. Document, obtain approval and communicate Roles & Responsibiities for all participants in the Metadata process 2. Align the roles within the established workstream and leverage documentation used for RESPA/TILA EOC | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst-BSC Business Metadata Lead Technical Metadata Lead Requirements Lead Data Quality Lead Data Analyst - Rqmts/Metadata MIDE/MODE Managers Business Intelligence Manager Release Manager Metadata Architects Program Manager | 300 | 24000 | TIER 2 | b. Improved operational, regulatory, and financial risk management by providing transparency of KDE data movement which enables data governance and reporting | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance 2. Understand, Measure, and Manage Risk – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 4. Grow Production Channels – Process and service will be our competitive advantage • Innovate and standardize production processes to deliver highly predictable service to customers
14. Governance - Risk Management | Capability | Metadata Reporting (lineage, completeness, etc.) Flexibility to utilize reporting to establish quantitative and qualitative Metadata measurement | 1. Identify the Quantitative and Qualitative Metrics required for Metadata quality 2. Conduct Validation Reporting POC 3. Leverage POC results to identify appropriate toolset, approach and resources required 4. Develop timeline for validation reporting effort 5. Build and deploy Metadata quality reports NOTE: Estimate assumes 10 initial reports of medium complexity | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Quality Lead Metadata Architects Program Manager | 905 | 65025 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 2. Understand, Measure, and Manage Risk – Integrate risk management deeply into our operations • Define, track, measure, and improve first-pass quality and defect rates – Strengthen our risk management culture • Promote and demonstrate an effective “raise your hand” culture • Operate within defined risk appetite standards, with preventative controls in place 5. Leverage the Enterprise – Leverage the technology, tools, and capabilities of the broader Enterprise to improve our ability to serve customers and clients
15. Governance - Data Asset Reuse | Capability | Lifecycle Management •New Terms (proposed, candidate, approved, deprecated, etc.) •Term Conflict management, overloading, context collision •New SOR data | 1. Define new and enhance existing Home Lending metadata governance processes, leveraging industry best practices 2. Communicate and deploy defined governance processes | Data Governance Manager DSG Technology Manager Technical Data Governance Lead Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmts/Metadata Metadata Architects Data Steward (DSO) Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification – Effectively translate investor, regulatory, and legal guidelines into policy and process
15. Governance - Data Asset Reuse | Capability | Data Asset Reuse: - Shared Dataset creation - Detailed level associations | 1. Identify existing shared data assets and opportunities for modifying data assets to make reusable 2. Establish standards to support ongoing reuse of data assets | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead MIDE/MODE Managers MIDE/MODE Developers Metadata Architects Program Manager | 300 | 24000 | TIER 2 | c. Enable data asset reuse to drive efficiency and cost reduction opportunities throughout the SDLC | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification
16. Usability - Locate Data Faster | Capability | Query/Report creation - Results grouped and ordered by tags | Develop & deploy a user-friendly query/reporting solution to provide rapid access to commonly needed Metadata information 1. Define business requirements for accessing metadata - include ability to group and order by tags - limit result set 2. Identify toolset and develop solution through POC - Engage users for trial and feedback 3. Develop timeline for deployment of final solution including end-user training | Data Governance Manager DSG Technology Manager Technical Data Governance Lead ED&A/EMM Manager ED&A/EMM Analyst Business Metadata Lead Technical Metadata Lead Requirements Lead Data Analyst - Rqmt/Metadata Business Intelligence Manager Business Intelligence Engineers Metadata Architects Program Manager | 1200 | 96000 | TIER 2 | a. Accelerate LOB adoption of strategic data platforms through information cataloging capabilities that allow end users to locate data faster | 1. Process and Customer Service Excellence, and Scale as Competitive Advantage – Develop and strengthen process management disciplines across our operations and organization • Establish clear process ownership, ownership expectations, and process governance • Architect holistically – people, process, technology, and data • Think horizontally and end-to-end – Use technology to drive process and experience innovation • Accelerate activities with trusted source data to substitute data for documents – Identify and execute on simplification opportunities • Accelerate product and program simplification 3. Enable the Best Team in the Mortgage Industry – We will deploy training, tools, and programs to enable and empower our customer-facing team members and supervisors/managers • Job-specific learning paths with clear expectations and documentation of knowledge transfer and proficiency – We will strengthen and improve the quality of our new hires • Strengthen on-boarding process with emphasis on Vision and Values